{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":22,"n_cols":7,"rows_kept":22,"cut":false,"hidden":false,"merged":[]}
["序号","工作模块","工作计划","细节说明","责任人","完成时间","备注说明"]
[1,"结构安全监测产品线","安心云4.0上线","安心云首页同步上线，优先升级同步业主展示侧，Q2完成集成管理侧","许苏炜","2022Q1，2022Q2"]
[2,"结构安全监测产品线","完成市政桥梁巡检评估系统，丰富产品形态",null,"许苏炜","2022Q1"]
[3,"智慧工地产品线","完成工程项目管理平台的研发和发布","Q1完成基础系统搭建，Q2逐步完善达成商业化应用","陈昌","2022Q2"]
[4,"企业综合管理产品线","流程绩效",null,"张文君","2022Q1"]
[5,"企业综合管理产品线","供应链管理系统","Q1完成基础框架搭建，Q2逐步完成产品管理、计划管理、自动算料","张文君","2022Q2"]
[6,"企业综合管理产品线","应用管理","实现表单、流程、页面、操作以低代码平台形式自助搭建各部门应用","张文君","2022Q2"]
[7,"企业综合管理产品线","数据仪表盘",null,"张文君","2022Q2"]
[8,"企业综合管理产品线","BI分析报表",null,"张文君","2022Q3"]
[9,"消防安防产品线","规划消防园区应用落地","在飞尚园区进行智慧消防/传统消防示范试点方案的设计和实施","刘付鹏","2022Q1"]
[10,"消防安防产品线","智慧消防建设推进","CCCF取证后，部分产品实现自产总装，并结合项目情况，消防数据分析/可视化/消防管理展示方向做深度开发，接入易用性方面也需要做进一步提升。","刘付鹏","2022Q2"]
[11,"家电产品线","车载空气净化器",null,"唐兵","2022Q1"]
[12,"家电产品线","自研空气净化器",null,"唐兵","2022Q2"]
[13,"家电产品线","桌面立式加湿器",null,"唐兵","2022Q2"]
[14,"IOT产品线","基于国标GB/T28181实现自研视频平台",null,"殷伟文","2022Q1"]
[15,"IOT产品线","IOT平台-业务剥离和自定义建模",null,"殷伟文","2022Q2"]
[16,"IOT产品线","数据湖/数据中台架构","包括存储、动态ETL、数据治理、数据资产化等","殷伟文","2022Q2"]
[17,"IOT产品线","边缘计算网关","替代高频振动采集等使用场景","殷伟文","2022Q3"]
[18,"IOT产品线","数据BI架构和数据分析工具",null,"殷伟文","2022Q3"]
[19,"前沿技术","数字孪生综合解决方案",null,"刘歆毅/数字孪生可视化小组","2022Q3"]
[20,"效率效能","梳理构建体系化的内部DevOps平台","包括：项目管理平台、持续集成、持续交付、镜像仓库、集群运维、容器编排、系统监控、代码审查、文档协同、自动化测试、状态预警等工具链","刘歆毅/DevOps效能小组","2022Q4","Q1完成项目管理平台（禅道）和协同工具落地\nQ2梳理DevOps过程链条形成内部平台\nQ3完成代码审查和系统监控\nQ4完成自动化测试"]
[21,"效率效能","优秀敏捷过程实践推广","面向产品线负责人和产品经理，组织培训交流，落实过程工具要求","刘歆毅","2022Q1"]