{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":41,"n_cols":27,"rows_kept":41,"cut":false,"hidden":false,"merged":[[0,0,1,9],[0,10,0,16],[0,17,1,23],[0,24,1,26],[1,10,1,12],[1,13,1,16]]}
["原始信息",{"$nulls":9},"过程信息",{"$nulls":6},"处理信息",{"$nulls":6},"变更信息"]
[{"$nulls":10},"需求是否可实现",null,null,"需求是否符合年度产品规划目标"]
["需求编号","需求说明","用户故事/图片说明","所属功能模块","需求类别","提出时间","接收人","是否评审","评审时间","需求来源","具有难度？","可行性？","风险？","改善产品功能？","改善产品性能？","增加用户满意度","增加产品竞争力","是否实现","优先级","交互原型","预计完成时间","产品及版本号","实际完成时间","未实现原因","是否出现变更","变更基线","变更记录"]
[1,"平台产品定义","1. 代码Fork。UI页产品名称修改\n2. 登录页定制和logo替换、copyright修改",null,"功能","2021.8.11",null,"否"]
[2,"整体架构文档","1. 整体架构\n2. 需求整理",null,"功能","2021.8.11",null,"否"]
[3,"产品官网原型设计","1. 原型/UI设计\n2. 官网页面开发",null,"功能","2021.8.11",null,"否"]
[4,"视频接入方案","1. 视频接入平台的整体方案",null,"功能","2021.8.11",null,"否"]
[5,"安心云服务端业务逻辑块梳理","1. 服务端代码梳理，输出业务独立代码位置。",null,"功能","2021.8.11",null,"否"]
[6,"Java中脚本调用预研","1. 预研输出Java调用脚本的方式",null,"功能","2021.8.11",null,"否"]
[7,"ETL整体改造设计","1. ETL详细设计方案（包括数据组织形式）\r\n2. ETL相关的数据库设计\r\n3. 接口钩子设计\r\n4. 脚本调用方式设计",null,"功能","2021.8.11",null,"否"]
[7,"ETL感知模型重构","1. 改写感知模型定义\n2. 模型访问DAO、Redis缓存定义",null,"功能","2021.8.11",null,"否"]
[8,"ETL设备数据入湖IceBerg","1. Table Schema设计\n2. Flink ET中处理设备数据，存储到数据湖",null,"功能","2021.8.11",null,"否"]
[9,"ETL接口钩子开发","1. 定义接口数据格式\n2. 钩子接口开发",null,"功能","2021.8.11",null,"否"]
[10,"ETL计算过程JS脚本支持开发","1. 定义脚本函数接口\n2. 脚本调用开发",null,"功能","2021.8.11",null,"否"]
[11,"WEB功能 -- 感知模型原型定义","1. 行业感知模型原型导入\n2. 自定义功能模型定义（扩展能力）\n3. 虚拟设备创建",null,"功能","2021.8.11",null,"否"]
[12,"WEB功能 -- 扩展设备感知能力","1. 部署完成之后，扩展设备感知能力（不同于安心云测点，这里可以选择不绑定）\n2. 设备绑定感知模型（公式选择、参数输入）\n3. 组合虚拟设备配置\n4. 设备分组配置",null,"功能","2021.8.11",null,"否"]
[13,"WEB功能 -- 视频接入","1. 视频接入配置页面\n2. Thing展示视频快照和实时视频流\n3. 控制云台",null,"功能","2021.8.11",null,"否"]
[14,"告警Alarm扩展","1. 支持告警逻辑判断hook调用\n2. 支持告警内容脚本定义",null,"功能","2021.8.11",null,"否"]
[15,"WEB功能迁移 -- 阈值设置","1. 阈值增删改\n2. 变化速率阈值增删改",null,"功能","2021.8.11",null,"否"]
[16,"告警Alarm推送修改","1.平台不保存告警策略.生成告警时通知各应用，应用判断推送内容分发策略，通过消息通知平台分发服务",null,"功能","2021.8.11",null,"否"]
[17,"WEB功能 -- 数据展示","1. 包含感知数据\n2. 原始数据展示从IceBerg中获取",null,"功能","2021.8.11",null,"否"]
[18,"WEB功能 -- 告警展示","1. 包含数据类告警\n2. 设备告警数据从IceBerg中获取",null,"功能","2021.8.11",null,"否"]
[19,"WEB功能迁移 -- 聚集配置","1. 聚集配置增删改",null,"功能","2021.8.11",null,"否"]
[20,"重计算修改","1. 从IceBerg中获取数据\n2. 执行重计算流程",null,"功能","2021.8.11",null,"否"]
[21,"WEB功能迁移 -- 数据计算页面","1. 重计算\n2. 异常过滤\n3. 异常数据识别",null,"功能","2021.8.11",null,"否"]
[22,"WEB功能迁移 -- 阈值设置","1. 代码组建\n22. 登录页定制和logo替换、copyright修改",null,"功能","2021.8.11",null,"否"]
[23,"WEB功能 -- 扩展公式计算","1. 公式计算分：内置、表达式、脚本\n2. 支持脚本录入、简单调试",null,"功能","2021.8.11",null,"否"]
[24,"WEB功能 -- 函数计算钩子设置接口","1. 支持设置ETL中指定流程位置钩子调用\n2. 设置钩子函数地址，调用规则参数等",null,"功能","2021.8.11",null,"否"]
[25,"设备协议解析优化","1.定义平台标准通用mqtt-json格式。实现标准java-sdk库作设备上的开发套件\n2.可选标准协议（modbus）\n3.可视化协议组件（协议组成选取指定类型解析、json格式字段映射配置）\n4.扩展目前支持的脚本类型",null,"功能","2021.8.11",null,"否"]
[26,"规则引擎扩展","1. 数据源扩展\n2. 输出方式扩展\n3. 扩展HTTP/MQTT输出规则的内容格式定义",null,"功能","2021.8.11",null,"否"]
[27,"通用数据推送","1. 标准Http输出格式。",null,"功能","2021.8.11",null,"否"]
[28,"场景联动","1.定义数据联动规则\n2.触发能力接口\n3.触发告警调用",null,"功能","2021.8.11",null,"否"]
[29,"影子设备定义","1. 低功耗设备配置影子副本\n2. 影子设备配置同步功能",null,"功能","2021.8.11",null,"否"]
[30,"数据透视","1. 时序透视 （包含页面自动聚集）\n2. 表格数据\n3. SQL分析（结合数据湖）",null,"功能","2021.8.11",null,"否"]
[31,"空间透视","1. 3D模型展示：\n2. 地理围栏：设置围栏和进出告警、\n3. 热力图 （设备数据、设备分布） （热成像和点聚合（平均、求和））\n4. 历史轨迹：生成一段时间的设备轨迹、进行播放",null,"功能","2021.8.11",null,"否"]
[32,"大屏展示套件","1. 提供默认大屏展示模板\n2. 数据展示配置定义",null,"功能","2021.8.11",null,"否"]
[33,"归档文件下载","数据湖中原始和感知数据归档文件下载",null,"功能","2021.8.11",null,"否"]
[34,"WEB:报表配置","1. 通用日报配置\n2. 立即生成",null,"功能","2021.8.11",null,"否"]
[35,"报表进程优化","1. 实现通用报表模板\n2. 实现通用报表数据接口(简化应用定制开发报表工作)",null,"功能","2021.8.11",null,"否"]
[36,"分析工具扩展","1. 支持从IceBerg中获取数据的接口",null,"功能","2021.8.11",null,"否"]
[37,"简化设备接入","1. 接入demo示范\n2. 接入流程向导指引",null,"功能","2021.8.11",null,"否"]